## Blank
Numbered
Activity
Numbered
Activity
Numbered
Activity
1: Define Objectives (1 Day)
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Numbered
Activity
Start
Start
End
End
Buffer
Buffer
4: Design Orientation Content (3 Days)
8: Conduct Orientation Sessions (2 Days)
5: Plan Campus Tour (2 Days)
7: Create Marketing Materials (2 Days)
3: Develop Project Charter (1 Day)
2: Identify Stakeholders (2 Days)
4 days
6: Arrange Catering (1 Day)
8 days
11.Gather Feedback (1 Day)
10.Facilitate Q&A Session (1 Day)
9.Provide Technical Support (1 Day)
5 days
12.Review and Analyze Feedback (2 Days)
13.Finalize Budget and Costs (1 Day)
14.Document Lessons Learned (1 Day)
4 days
End