## Blank
Resource Breakdown Structure Project Name: Date:
WBS Identifier # | Work Package | Internal Personal Required | External Personnel Required | Venue Costs | Materials Required | Supplies Required | Equipment Required | Comments | Total Direct Costs
1.1.1 | Project Planning
1.1.2 | Define Objectives | 2 hours | [5 empty] | Initial Planning | $100
1.1.3 | Identify Stakeholders
1.1.4 | Develop Project Charter
1.2.1 | Program Development
1.2.2 | Design Orientation Content | 10 hours |  |  | $500 |  |  | Content Creation | $500
1.2.3 | Plan Campus Tour
1.2.4 | Arrange Catering
1.2.5 | Create Marketing Materials
1.3.1 | Implementation
1.3.2 | Conduct Orientation Sessions | 20 hours |  | $500 |  |  | $1200 | Includes technical setup | $1700
1.3.3 | Provide Technical Support
1.3.4 | Facilitate Q&A Session
1.3.5 | Gather Feedback
1.4.1 | Project Closure
1.4.2 | Review and Analyze Feedback
1.4.3 | Finalize Budget and Costs
1.4.4 | Document Lessons Learned
TOTAL COSTS |  | 0 | 0 | $500 | $500 | 0 | $1200 | 0 | $2300
Contingency Requirements (10%) | [8 empty] | 230
Personnel Cost Requirements | [5 empty] | Note: Update Cost Categories to reflect actual project requirements
Rate | Name | Hours | Costs
0
0
0
0
0
0
0
0
TOTAL |  |  | 0

## Demo Example
Resource Breakdown Structure: "Hierarchical breakout of resources by category and type" Project Name: Annual Executive Meeting Support Project Date: 30 April 20XX
WBS Identifier # | Work Package | Personnel Costs | Beverage Costs | Catering Costs | Support Costs | Venue Support | Comments | Total Direct Costs
1.1.1 | Define Venue |  |  |  |  | 1000 | Initial Deposit | 1000
1.1.2 | Determine Attendees |  |  |  | 1500 |  | Handouts/Print | 1500
1.1.3 | Plan Team | [6 empty] | 0
1.1.4 | Plan Beverages |  | 500 |  |  |  | Coffee/Juice | 500
1.1.5 | Plan Catering |  |  | 1000 |  |  | Box Lunches | 1000
2.1.1 | Assemble Packages | [6 empty] | 0
2.1.2 | Install AV | [6 empty] | 0
2.1.3 | Set Up Venue | [6 empty] | 0
2.1.4 | Conduct Meet |  |  |  | 1000 |  | AV/IT Support | 1000
3.1.1 | Close Out Venue | 600 |  |  |  | 1000 | Clean/Venue $ | 1600
3.1.2 | Prepare Final Reports | [6 empty] | 0
3.1.3 | Pay Outstanding Invoices | 30 |  |  |  |  | Bookkeeper | 30
3.1.4 | Perform Lessons Learned | [6 empty] | 0
TOTAL COSTS |  | 630 | 500 | 1000 | 2500 | 2000 | 0 | 6630
Contingency Requirements (10%) | [7 empty] | 663